## Sheet2
MCI Project Weekly Time Sheet
Team | CI4 | Student ID |  | a1894836 |  | Week starting: | 17/3/2025 (Week 3)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 17/3/25 | 10:30 | 15:30 | 5 | UI design and calibre | requirement learning | mockup UI
Tuesday | 18/3/25 | 15:00 | 16:30 | 1.5 | supervisor meeting | confirm project scope/features | confirm possible project ideas
Wednesday | 19/3/25 | 11:00 | 14:30 | 3.5 | finalize architecture | team collaboration | tech stack confirmed
Thursday | 20/3/25 | 4:00 | 18:30 | 2.5 | research for LLM selection | technical prep | test API keys
Friday | 21/3/25 | 13:00 | 16:30 | 3.5 | Github workflow update | previous work synchronize | code update
Saturday | 22/3/25 | 12:00 | 14:00 | 2 | code refactoring | code revision | workflow enhancement
|  |  | Total | 18