## Sheet2
MCI Project Weekly Time Sheet
Team | CI4 | Student ID | a1909438 |  |  | Week starting: | 3/17/2025(W3)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-03-17 | 9:30 | 13:30 | 4 | React UI design learning | Skill building | Mock up UI
Tuesday | 2025-03-18 | 15:00 | 16:30 | 1.5 | Supervisor meeting | Confirm use cases/features | Move to architecture
Wednesday | 2025-03-19 | 10:00 | 13:30 | 3.5 | Tech stack preparation & confirmation | Team alignment | Finalize stack choices
Thursday | 2025-03-20 | 14:00 | 17:00 | 3 | Study and prepare for LLM API keys | Technical foundation/prep | Obtain/test API keys
Friday | 2025-03-21 | 14:00 | 17:30 | 3.5 | Initialize GitHub framework | Code initialization | Push initial code
Saturday | 2025-03-22 | 10:00 | 13:30 | 3.5 | Refactor initial code & review architectural logic | Code improvement | Enhance structure
|  |  | Total | 19